## Slide 1
LG SOFT INDIA · 12-MONTH INDUSTRY PROJECT
Privacy-Preserving Collaborative
Intrusion Detection for the IoV
Federated learning with CKKS homomorphic encryption
Month 5 status update
Federated Learning · Homomorphic Encryption · Byzantine Robustness
Notes: Month 5 of 12. Headline: the month became an audit-then-rebuild. We found seven defects that invalidated earlier results, fixed all of them, and then went back and closed three deliverables from Months 1-4 that had never been started.

## Slide 2
Where we stand
End of Month 5 of 12
5 / 12
months elapsed
7 / 8
deliverables due by
Month 4 now closed
105
automated correctness
assertions, all passing
1
blocker, and it is
procurement
Headline
Encryption costs no accuracy. Across all four datasets the encrypted and plaintext runs agree to within seed variance — and the server never decrypted a single individual vehicle update.
Cryptography and machine-learning tracks are healthy and one item is ahead of schedule. The embedded/hardware track is the whole of the remaining gap.
Notes: Lead with this slide. Four numbers, then the headline. The one blocker is that no hardware has been ordered - everything else on the embedded track is now software-complete and waiting on a board.

## Slide 3
What Month 5 became
It started as multi-key CKKS research. An audit changed the plan.
1
We audited the whole project before building on it
Standard practice before adopting a new cryptographic scheme: check the foundation first.
2
The audit found seven defects — several invalidated our headline results
The encryption in the training loop was not encryption. The Byzantine filter decrypted every vehicle's update. CAN labels came from filenames.
3
So Month 5 became: fix the foundation, then build on it
All seven fixed and machine-verified. Then real CKKS, FheFL aggregation and multi-key sharing on top.
4
Then we went back and closed three Month 1–4 deliverables
Packing module, NTT implementation and the hardware benchmark harness — none had been started.
Notes: Be straightforward about this. Finding the defects was the valuable part - had we built multi-key CKKS on top of a leaky pipeline we would have produced a cryptographically elegant result about nothing.

## Slide 4
The seven defects — all fixed and verified
Each is now guarded by an automated test, so it cannot silently return
# | What was wrong | Why it mattered | Status
D1 | Labels came from the source filename, not ground truth | Trained a capture-file classifier, not an IDS. Caused the 100% accuracy | Fixed
D2 | 75%-overlapping windows split randomly across train/test | Test accuracy measured memorisation, not generalisation | Fixed
D3 | FHE-vs-plaintext was not a controlled experiment | Produced a spurious 5-point accuracy gap that was pure divergence | Fixed
D4 | The server decrypted every individual client update | Voided the central privacy claim of the entire project | Fixed
D5 | VeReMi windowed across mixed senders | Label was near-random; model was fine. Needs data re-acquisition | Diagnosed
D6 | Transport security had been removed in Month 4 | FHE gives no authentication, integrity or replay protection | Fixed
D7 | Documentation contradicted the code | Three months of drift | Fixed
Notes: D4 is the one to emphasise: the deck said the server never sees plaintext, and the code decrypted every client's full 44,164-parameter update every round. That is now a machine-checked invariant, asserted after every round.

## Slide 5
Results — does encryption cost accuracy?
3 seeds · 10 simulated vehicles · 5 federated rounds · Dirichlet alpha = 0.3
Dataset | CKKS encrypted | Plaintext baseline | Difference | Verdict
CAN-VTC | 1.0000 ± 0.0000 | 1.0000 ± 0.0000 | 0.0000 | within seed noise
Car-Hacking | 0.9977 ± 0.0012 | 0.9981 ± 0.0006 | −0.0004 | within seed noise
CICIDS-2017 | 0.9555 ± 0.0079 | 0.9542 ± 0.0098 | +0.0013 | within seed noise
VeReMi | 0.4839 ± 0.0433 | 0.4851 ± 0.0424 | −0.0012 | within seed noise
Conclusion
CKKS introduces ~1e-8 of numerical error — six orders of magnitude below the noise already in SGD. Encryption is free in accuracy terms.
Read honestly
Car-Hacking is the meaningful benchmark. CAN-VTC is trivially separable (51% flood density). VeReMi is near-chance — its export lost the sender ID.
Notes: The Month-4 setup was structurally incapable of answering this question, because its simulated encryption injected noise that sent the two arms down different training trajectories. This is the first controlled version of the comparison.

## Slide 6
Encrypted versus plaintext, side by side
Bars are indistinguishable on every dataset — that is the result
Chart: 
| CAN-VTC | Car-Hacking | CICIDS-2017 | VeReMi
CKKS encrypted | 1 | 0.9977 | 0.9555 | 0.4839
Plaintext baseline | 1 | 0.9981 | 0.9542 | 0.4851
Privacy invariant
0
individual vehicle updates decrypted by the server, across every run
VeReMi is near chance
Its attacks are defined by how a sender's claims change over time, and the cleaned export dropped the sender ID. Neither formulation can express the task. Needs re-acquisition.
Notes: If asked why VeReMi is low: we measured it before training. Best single-feature class separation is 0.046 standard deviations - the features cannot express the task. Training then confirmed it at ROC-AUC 0.516.

## Slide 7
What we built in Month 5
Real cryptography replacing a simulation
A
Real CKKS encryption
The Month-4 'encryption' was a numpy array plus 1e-9 noise. Now genuine TenSEAL ciphertexts, 2.47 MB per vehicle per round.
B
FheFL robust aggregation
Outliers scored by encrypted distance to the previous global model, then down-weighted — never excluded, never decrypted.
C
Multi-key key sharing
The decryption key is never assembled. Recovering one vehicle's update needs collusion with U−1 others.
D
A fix the paper does not have
Masks only cancel if every keyed vehicle reports in — one offline breaks decryption. We re-scope per round.
E
Transport security restored
ECDH-P256 + AES-256-GCM + Ed25519. FHE gives confidentiality only — not authentication, integrity or replay protection.
F
105 automated assertions
Three suites gating every result: labelling, split disjointness, and the cryptographic invariants.
Notes: Point D is our own contribution beyond the paper. FheFL samples a random subset of users each round but generates pairwise secrets once at enrolment - so any dropout breaks decryption silently. For a vehicle fleet that is the normal case, not an edge case.

## Slide 8
Then we closed three older deliverables
Months 1–4 items that had never been started
Deliverable | Due | What we delivered | Status
Optimized packing & encoding module | M3–4 | 29.6% lossless bandwidth reduction — 3.51 MB down to 2.47 MB per vehicle | Complete
High-performance NTT implementation | M3–4 | Negacyclic NTT, validated exactly against a reference oracle. 11.22× over an optimised baseline. Test vectors exported for the C port | Reference done
Baseline benchmarking on hardware | M1–2 | Portable harness plus a full host baseline. The target-board run is the only missing piece | Harness done
Deliverables due by end of Month 4: 5 of 8 → 7 of 8
Notes: These were genuinely not started before this month. The packing win came from reading the protocol rather than the cryptography - the server's two operations act on independent copies of each ciphertext, so the update only needs one multiplicative level, not two.

## Slide 9
Two measured engineering results
Both reproducible from the repository
Bandwidth
29.6%
smaller uploads, at zero accuracy cost
3.51 MB → 2.47 MB per vehicle per round
Found by analysing the protocol, not the crypto
The server's two operations use independent copies, so only one multiplicative level is needed — not two
NTT kernel
11.22×
faster than an optimised O(N²) baseline
The hottest kernel in any FHE library
Our first version was slower than naive — it made ~8,191 tiny calls per transform
Batching each stage made it 53× faster. Lesson: memory pattern dominates, not arithmetic
Notes: The NTT lesson transfers directly to the embedded port: performance is governed by memory access pattern and per-operation overhead, not by the butterfly arithmetic. That is why the production kernel needs contiguous SIMD lanes rather than a literal transcription of the pseudocode.

## Slide 10
What we are not claiming
Stated up front so nothing reads as an overclaim
1
This is not full multi-key CKKS yet
The homomorphic arithmetic is real. The multi-key key management is an algebraic model, because TenSEAL exposes no multi-key API. Migrating to OpenFHE closes this — it is the Month-6 priority.
2
Nothing has run on target hardware
The NTT reference, packing module and benchmark harness are all built and validated, but every number was measured on a development laptop.
3
Byzantine robustness is untested against patient attackers
Our scoring rewards staying close to the consensus, so a low-magnitude persistent attacker is an open blind spot. The experiment is scheduled for Month 6.
4
One dataset contributes nothing until re-acquired
VeReMi's cleaned export dropped the sender ID, and its attacks are defined over time per sender. We measured this before training and training confirmed it.
Notes: Being explicit here is deliberate. Every one of these has a dated plan attached. Raising them ourselves is better than having them found in review.

## Slide 11
The one thing blocking us
Every remaining Month 1–4 item is blocked on the same thing, and nothing else
No target hardware has been ordered
The embedded track is now software-complete and waiting on a board. Ordering one is about an hour of work.
What we are asking for
NXP S32G evaluation board
The realistic production target — an automotive network processor built for vehicle gateways.
Raspberry Pi 5 — available this week
An interim ARM host. Removes procurement delay from the critical path so cross-compilation and NTT profiling can start immediately.
Notes: This is the ask. The Pi is the important half - it is inexpensive and it unblocks the work now, while the automotive board is sourced. Without a board, months 7-12 (hardware-in-the-loop, power audit) cannot start either.

## Slide 12
Month 6 plan
In priority order
Priority | Task | Effort | Why it is ranked here
P0 | Order target hardware | 1 hour | Unblocks the entire embedded track
P0 | Bind round number into the channel; enforce noise flooding | 3 hours | Closes replay and an approximate-decryption exposure
P1 | Migrate to OpenFHE | 12 days | The only way to make multi-key CKKS real — TenSEAL cannot express it
P1 | Low-magnitude poisoning experiment | 3 days | Tests our known blind spot in Byzantine robustness
P1 | Scale to 50 vehicles / 50 rounds | 4 days | Moves toward the roadmap target of 50–200
P1 | Re-acquire VeReMi with sender IDs | 2 days | Restores a dataset that currently contributes nothing
The embedded track shrank from ~40 days to ~22 this month, and the on-hardware benchmark from 2 days to half a day.
Notes: OpenFHE is the biggest single item and the most important. Until it lands we should not describe the system as full multi-key CKKS in any writeup.

## Slide 13
Summary
Audited the project and fixed seven defects
All machine-verified by 105 automated assertions
Replaced simulated encryption with real CKKS
And showed encryption costs no accuracy
Closed three Month 1–4 deliverables
7 of 8 now complete, up from 5 of 8
One blocker remains: order a board
The embedded track is software-complete and waiting
github.com/hithesh2205/LG-IoV
Full documentation: 27-page master PDF + 16 supporting documents in the repository
Notes: Close on the ask. Everything else is on track and documented; the board is the one decision we need from this meeting.